## ITS
2021 NOVEMBER INDICATOR TRACKER SHEET
MONDAY 1ST NOVEMBER TO TUESDAY 30TH OVEMBER 2021
Prepared by : ABDULSAMAD, Abbas Salihu
abdulsamadabbas1439@gmail.com, abdulsamadabbas@yahoo.com
(+234) 8126709076 ¦ (+234) 9056639934
S/N | INDICATOR | SOURCE OF DATA | MEASUREMENT | LOA TARGET | STATUS | HOW FAR | REMARK
1 | Outpatient consultations per person per year (Utilization Rate) | Health Facility NHMIS (OPD Register) 4th Quarter | 2.1127 | 0.5 | TARGET ACHIEVED | 422.5% | The utilization rate at the supported health facility is quite high acording to the NHMIS register, outpatient consultations are measured at about 2 per person in the month of November 2022.
-1.6127
2 | % of women attending at least 4 ANC clinics | Health Facility HMIS 4th Quarter | 4.3513 | 17600 | NOT ACHIEVED | 0.02472% | Only 4 women attended atleat 4 ANC at supported facility in November 2022, the project has not affected the ANC attendance for the month of November
[6 empty] | 17595.6487 | We need about 17,600 ANC attendance to breakeven
3 | % of health facilities submitting DHIS2 reports timely. | DHIS2 Platform 4th Quarter | 0.1939% | 80% | NOT ACHIEVED | 0.2424% | According to the LOA target, 0% of health facilities submitted DHIS2 reports timely
79.81%
4 | % of children <1yrs who received their third dose of DPT-containing vaccine | Health Facility HMIS (Immunization registers) | 0.68078 | 43900 | NOT ACHIEVED | 0.001551% | only minute number of children received third dose of immunization both at fixed post and outreach according to the data for the month of November. 0% is achieved compared to the LOA targets
43899.3192
5 | # of outpatient curative consultations | Health Facility HMIS (OPD registers) | 18523 | 439000 | NOT ACHIEVED | 4.219% | 18,523 outpatient ccurative consultations was recorded on OPD registers and it is only 4% of progress moving toward the LOA target
420477

## Catchment_Pop
Name of Health Facility | LGA | State | Catchement Population
bo Abbaganaram Maternal and Child Health Centre | MMC | Borno | 45007
bo Banki Health Clinic | Bama | Borno | 22044
bo Bulabulin Primary Health Care Centre | MMC | Borno | 44850
bo Dalori Primary Health Care Centre | Konduga | Borno | 13200
bo Bama Skin Clinic | Bama | Borno | 28400
bo Gomari Primary Health Centre | Jere | Borno | 39200
bo Chad Basin Development Authority Clinic | Jere | Borno | 55500
bo kaleri primary Health Centre | Mafa | Borno | 59454
bo Izge Primary Health Care Clinic | Gwoza | Borno | 14595
bo Jakana Model Primary Health Care Center | Konduga | Borno | 49610
bo Mafa Primary Health Centre | Mafa | Borno | 48700
bo Maimusari Health Clinic | Jere | Borno | 56432
bo Mala Kachallah Primary Health Centre | MMC | Borno | 111989
bo Malakyariri Primary Health Centre | Mafa | Borno | 53256
bo Bama Maternal and Child Referral center | Bama | Borno | 24000
bo Nguwom Primary Health Center | Mafa | Borno | 5940
bo Pompomari Primary Health Care Centre | Konduga | Borno | 26400
bo Zabbarmari Health Clinic | Jere | Borno | 18640
bo Monguno Primary Health Care Center | Monguno | Borno | 159542
876759
17535.18
3653.1625
Using the attached indicator reference document as a guide and the information provided in the first 2 sheets of the attached workbook, prepare an indicator tracking sheet that shows the progress (as at November 2022) of 3 out of the 3 indicators on the Indicator reference document. Assume that the life of the project is one year (January 2022 to December 2022) – 20 marks

## Data_ext
periodname | organisationunitname | ANC 4th visit | Out-patient Attendance | Penta 3 given <1y, Fixed | Penta 3 given <1y, Outreach | NHMIS Monthly Summary Form (Version 2019) - Reporting rate on time
January 2022 | bo Abbaganaram Maternal and Child Health Centre | 18 | 237 | 54 | 10 | 0
January 2022 | bo Bulabulin Primary Health Care Centre | 3 | 477 | 22 | 9 | 0
January 2022 | bo Mala Kachallah Primary Health Centre | 46 | 367 | 106 | 30 | 100
January 2022 | bo Dalori Primary Health Care Centre | 20 | 208 | 7 | 3 | 100
January 2022 | bo Mafa Primary Health Centre | 15 | 1154 | 207 | 40 | 0 | Row Labels | Sum of ANC 4th visit | Sum of Out-patient Attendance | Sum of NHMIS Monthly Summary Form (Version 2019) - Reporting rate on time | Sum of Penta 3 given <1y, Outreach | Sum of Penta 3 given <1y, Fixed
January 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 0 | November 2022 | 763 | 18523 | 1700 | 521 | 1966
January 2022 | bo Malakyariri Primary Health Centre | 20 | 273 | 77 | 37 | 0 | Grand Total | 763 | 18523 | 1700 | 521 | 1966
January 2022 | bo Gomari Primary Health Centre | 19 | 276 | 51 | 19 | 100
January 2022 | bo Chad Basin Development Authority Clinic | 21 | 873 | 153 | 22 | 100
January 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
January 2022 | bo Nguwom Primary Health Center | 21 | 337 | 14 | 13 | 0
January 2022 | bo Maimusari Health Clinic | 21 | 873 | 153 | 22 | 100
January 2022 | bo Izge Primary Health Care Clinic | 21 | 873 | 153 | 22 | 0
January 2022 | bo Pompomari Primary Health Care Centre | 53 | 550 | 55 | 20 | 100
January 2022 | bo Zabbarmari Health Clinic | 49 | 1370 | 104 | 24 | 100
January 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
January 2022 | bo Jakana Model Primary Health Care Center | 11 | 370 | 13 | 8 | 100
January 2022 | bo kaleri primary Health Centre | 12 | 767 | 85 | 36 | 0
January 2022 | bo Bama Maternal And Child Referral center | 8 | 974 | 15 | 30 | 100
February 2022 | bo Abbaganaram Maternal and Child Health Centre | 25 | 261 | 34 | 5 | 0
February 2022 | bo Bulabulin Primary Health Care Centre | 4 | 361 | 25 | 9 | 0
February 2022 | bo Mala Kachallah Primary Health Centre | 38 | 210 | 96 | 38 | 0
February 2022 | bo Dalori Primary Health Care Centre | 49 | 718 | 16 | 12 | 100
February 2022 | bo Mafa Primary Health Centre | 12 | 881 | 199 | 39 | 100
February 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 0
February 2022 | bo Malakyariri Primary Health Centre | 9 | 466 | 87 | 49 | 100
February 2022 | bo Gomari Primary Health Centre | 17 | 522 | 39 | 13 | 100
February 2022 | bo Chad Basin Development Authority Clinic | 21 | 873 | 153 | 22 | 100
February 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
February 2022 | bo Nguwom Primary Health Center | 10 | 380 | 23 | 15 | 100
February 2022 | bo Maimusari Health Clinic | 52 | 247 | 188 | 8 | 100
February 2022 | bo Izge Primary Health Care Clinic | 26 | 484 | 29 | 30 | 100
February 2022 | bo Pompomari Primary Health Care Centre | 64 | 572 | 54 | 31 | 100
February 2022 | bo Zabbarmari Health Clinic | 21 | 873 | 153 | 22 | 100
February 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
February 2022 | bo Jakana Model Primary Health Care Center | 8 | 431 | 20 | 5 | 100
February 2022 | bo kaleri primary Health Centre | 9 | 887 | 85 | 52 | 100
February 2022 | bo Bama Maternal And Child Referral center | 7 | 1891 | 16 | 49 | 100
March 2022 | bo Abbaganaram Maternal and Child Health Centre | 42 | 460 | 48 | 8 | 0
March 2022 | bo Bulabulin Primary Health Care Centre | 8 | 705 | 29 | 10 | 0
March 2022 | bo Mala Kachallah Primary Health Centre | 72 | 332 | 150 | 70 | 0
March 2022 | bo Dalori Primary Health Care Centre | 29 | 691 | 17 | 14 | 100
March 2022 | bo Mafa Primary Health Centre | 19 | 1243 | 197 | 36 | 100
March 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
March 2022 | bo Malakyariri Primary Health Centre | 13 | 832 | 94 | 33 | 100
March 2022 | bo Gomari Primary Health Centre | 21 | 873 | 153 | 22 | 100
March 2022 | bo Chad Basin Development Authority Clinic | 32 | 1200 | 116 | 9 | 100
March 2022 | bo Bama Skin Clinic | 10 | 1396 | 70 | 15 | 100
March 2022 | bo Nguwom Primary Health Center | 2 | 464 | 18 | 27 | 100
March 2022 | bo Maimusari Health Clinic | 27 | 153 | 185 | 7 | 100
March 2022 | bo Izge Primary Health Care Clinic | 36 | 158 | 34 | 12 | 100
March 2022 | bo Pompomari Primary Health Care Centre | 66 | 1440 | 68 | 12 | 100
March 2022 | bo Zabbarmari Health Clinic | 12 | 868 | 85 | 36 | 100
March 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
March 2022 | bo Jakana Model Primary Health Care Center | 9 | 333 | 12 | 10 | 100
March 2022 | bo kaleri primary Health Centre | 10 | 571 | 110 | 26 | 100
March 2022 | bo Bama Maternal And Child Referral center | 6 | 2202 | 29 | 30 | 100
April 2022 | bo Abbaganaram Maternal and Child Health Centre | 69 | 2963 | 54 | 24 | 0
April 2022 | bo Bulabulin Primary Health Care Centre | 21 | 873 | 153 | 22 | 0
April 2022 | bo Mala Kachallah Primary Health Centre | 35 | 294 | 100 | 51 | 100
April 2022 | bo Dalori Primary Health Care Centre | 7 | 599 | 22 | 18 | 100
April 2022 | bo Mafa Primary Health Centre | 17 | 42 | 183 | 46 | 100
April 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
April 2022 | bo Malakyariri Primary Health Centre | 6 | 447 | 73 | 33 | 100
April 2022 | bo Gomari Primary Health Centre | 19 | 429 | 37 | 12 | 100
April 2022 | bo Chad Basin Development Authority Clinic | 21 | 873 | 153 | 22 | 100
April 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 0
April 2022 | bo Nguwom Primary Health Center | 49 | 412 | 16 | 24 | 100
April 2022 | bo Maimusari Health Clinic | 21 | 161 | 185 | 10 | 100
April 2022 | bo Izge Primary Health Care Clinic | 8 | 157 | 40 | 21 | 0
April 2022 | bo Pompomari Primary Health Care Centre | 45 | 419 | 64 | 15 | 100
April 2022 | bo Zabbarmari Health Clinic | 42 | 1375 | 142 | 43 | 100
April 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
April 2022 | bo Jakana Model Primary Health Care Center | 12 | 341 | 14 | 7 | 100
April 2022 | bo kaleri primary Health Centre | 1 | 990 | 40 | 15 | 100
April 2022 | bo Bama Maternal And Child Referral center | 8 | 2130 | 25 | 22 | 0
May 2022 | bo Abbaganaram Maternal and Child Health Centre | 22 | 410 | 48 | 10 | 100
May 2022 | bo Bulabulin Primary Health Care Centre | 4 | 1021 | 28 | 7 | 100
May 2022 | bo Mala Kachallah Primary Health Centre | 45 | 306 | 111 | 74 | 100
May 2022 | bo Dalori Primary Health Care Centre | 3 | 440 | 16 | 39 | 0
May 2022 | bo Mafa Primary Health Centre | 27 | 480 | 197 | 55 | 100
May 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
May 2022 | bo Malakyariri Primary Health Centre | 7 | 941 | 98 | 59 | 100
May 2022 | bo Gomari Primary Health Centre | 16 | 444 | 54 | 19 | 100
May 2022 | bo Chad Basin Development Authority Clinic | 19 | 850 | 156 | 6 | 100
May 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
May 2022 | bo Nguwom Primary Health Center | 4 | 360 | 53 | 17 | 100
May 2022 | bo Maimusari Health Clinic | 11 | 175 | 189 | 8 | 100
May 2022 | bo Izge Primary Health Care Clinic | 19 | 723 | 37 | 15 | 100
May 2022 | bo Pompomari Primary Health Care Centre | 58 | 494 | 64 | 22 | 100
May 2022 | bo Zabbarmari Health Clinic | 19 | 897 | 85 | 31 | 100
May 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
May 2022 | bo Jakana Model Primary Health Care Center | 21 | 304 | 15 | 11 | 100
May 2022 | bo kaleri primary Health Centre | 7 | 824 | 52 | 194 | 100
May 2022 | bo Bama Maternal And Child Referral center | 5 | 1743 | 29 | 35 | 100
June 2022 | bo Abbaganaram Maternal and Child Health Centre | 28 | 434 | 44 | 12 | 0
June 2022 | bo Bulabulin Primary Health Care Centre | 21 | 873 | 153 | 22 | 0
June 2022 | bo Mala Kachallah Primary Health Centre | 68 | 130 | 92 | 53 | 0
June 2022 | bo Dalori Primary Health Care Centre | 4 | 282 | 34 | 34 | 100
June 2022 | bo Mafa Primary Health Centre | 30 | 1298 | 178 | 54 | 100
June 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
June 2022 | bo Malakyariri Primary Health Centre | 11 | 818 | 69 | 63 | 100
June 2022 | bo Gomari Primary Health Centre | 21 | 873 | 153 | 22 | 100
June 2022 | bo Chad Basin Development Authority Clinic | 36 | 1820 | 108 | 7 | 100
June 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
June 2022 | bo Nguwom Primary Health Center | 6 | 444 | 27 | 33 | 100
June 2022 | bo Maimusari Health Clinic | 21 | 873 | 153 | 22 | 100
June 2022 | bo Izge Primary Health Care Clinic | 7 | 155 | 31 | 26 | 100
June 2022 | bo Pompomari Primary Health Care Centre | 46 | 2154 | 67 | 18 | 100
June 2022 | bo Zabbarmari Health Clinic | 34 | 746 | 103 | 28 | 100
June 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
June 2022 | bo Jakana Model Primary Health Care Center | 48 | 357 | 22 | 14 | 100
June 2022 | bo kaleri primary Health Centre | 20 | 320 | 130 | 111 | 100
June 2022 | bo Bama Maternal And Child Referral center | 9 | 1864 | 22 | 40 | 100
July 2022 | bo Abbaganaram Maternal and Child Health Centre | 14 | 235 | 18 | 4 | 100
July 2022 | bo Bulabulin Primary Health Care Centre | 3 | 767 | 19 | 7 | 0
July 2022 | bo Mala Kachallah Primary Health Centre | 31 | 256 | 76 | 67 | 100
July 2022 | bo Dalori Primary Health Care Centre | 2 | 526 | 21 | 23 | 100
July 2022 | bo Mafa Primary Health Centre | 9 | 459 | 195 | 35 | 100
July 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
July 2022 | bo Malakyariri Primary Health Centre | 16 | 1003 | 76 | 21 | 100
July 2022 | bo Gomari Primary Health Centre | 9 | 258 | 33 | 12 | 100
July 2022 | bo Chad Basin Development Authority Clinic | 64 | 1425 | 102 | 6 | 100
July 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
July 2022 | bo Nguwom Primary Health Center | 3 | 527 | 16 | 41 | 100
July 2022 | bo Maimusari Health Clinic | 21 | 873 | 153 | 22 | 100
July 2022 | bo Izge Primary Health Care Clinic | 13 | 1975 | 40 | 28 | 100
July 2022 | bo Pompomari Primary Health Care Centre | 36 | 674 | 66 | 13 | 100
July 2022 | bo Zabbarmari Health Clinic | 41 | 800 | 206 | 70 | 100
July 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
July 2022 | bo Jakana Model Primary Health Care Center | 11 | 394 | 17 | 11 | 100
July 2022 | bo kaleri primary Health Centre | 6 | 602 | 24 | 124 | 100
July 2022 | bo Bama Maternal And Child Referral center | 21 | 873 | 153 | 22 | 100
August 2022 | bo Abbaganaram Maternal and Child Health Centre | 31 | 812 | 55 | 5 | 100
August 2022 | bo Bulabulin Primary Health Care Centre | 2 | 1145 | 31 | 9 | 100
August 2022 | bo Mala Kachallah Primary Health Centre | 75 | 596 | 91 | 66 | 100
August 2022 | bo Dalori Primary Health Care Centre | 19 | 755 | 26 | 29 | 100
August 2022 | bo Mafa Primary Health Centre | 13 | 2569 | 202 | 73 | 0
August 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
August 2022 | bo Malakyariri Primary Health Centre | 9 | 1036 | 46 | 73 | 100
August 2022 | bo Gomari Primary Health Centre | 34 | 334 | 61 | 37 | 100
August 2022 | bo Chad Basin Development Authority Clinic | 138 | 1578 | 137 | 12 | 100
August 2022 | bo Bama Skin Clinic | 1 | 730 | 89 | 225 | 0
August 2022 | bo Nguwom Primary Health Center | 2 | 1648 | 30 | 54 | 100
August 2022 | bo Maimusari Health Clinic | 41 | 153 | 219 | 7 | 100
August 2022 | bo Izge Primary Health Care Clinic | 18 | 91 | 31 | 26 | 100
August 2022 | bo Pompomari Primary Health Care Centre | 82 | 1449 | 74 | 10 | 100
August 2022 | bo Zabbarmari Health Clinic | 73 | 1047 | 119 | 45 | 100
August 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
August 2022 | bo Jakana Model Primary Health Care Center | 26 | 315 | 29 | 29 | 100
August 2022 | bo kaleri primary Health Centre | 21 | 931 | 47 | 131 | 0
August 2022 | bo Bama Maternal And Child Referral center | 21 | 873 | 153 | 22 | 0
September 2022 | bo Abbaganaram Maternal and Child Health Centre | 47 | 7265 | 41 | 8 | 100
September 2022 | bo Bulabulin Primary Health Care Centre | 11 | 1278 | 22 | 3 | 100
September 2022 | bo Mala Kachallah Primary Health Centre | 61 | 257 | 75 | 32 | 100
September 2022 | bo Dalori Primary Health Care Centre | 7 | 674 | 26 | 19 | 100
September 2022 | bo Mafa Primary Health Centre | 22 | 3090 | 144 | 85 | 100
September 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
September 2022 | bo Malakyariri Primary Health Centre | 20 | 1231 | 69 | 42 | 0
September 2022 | bo Gomari Primary Health Centre | 24 | 424 | 33 | 10 | 100
September 2022 | bo Chad Basin Development Authority Clinic | 141 | 1784 | 127 | 6 | 100
September 2022 | bo Bama Skin Clinic | 1 | 404 | 89 | 225 | 100
September 2022 | bo Nguwom Primary Health Center | 5 | 993 | 22 | 2 | 100
September 2022 | bo Maimusari Health Clinic | 38 | 213 | 199 | 6 | 100
September 2022 | bo Izge Primary Health Care Clinic | 18 | 19 | 33 | 27 | 100
September 2022 | bo Pompomari Primary Health Care Centre | 54 | 2554 | 76 | 9 | 100
September 2022 | bo Zabbarmari Health Clinic | 50 | 789 | 132 | 25 | 100
September 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
September 2022 | bo Jakana Model Primary Health Care Center | 7 | 500 | 27 | 14 | 100
September 2022 | bo kaleri primary Health Centre | 5 | 993 | 25 | 59 | 0
September 2022 | bo Bama Maternal And Child Referral center | 21 | 873 | 153 | 22 | 100
October 2022 | bo Abbaganaram Maternal and Child Health Centre | 21 | 1312 | 34 | 26 | 0
October 2022 | bo Bulabulin Primary Health Care Centre | 9 | 1099 | 19 | 5 | 0
October 2022 | bo Mala Kachallah Primary Health Centre | 43 | 663 | 84 | 45 | 0
October 2022 | bo Dalori Primary Health Care Centre | 21 | 873 | 153 | 22 | 100
October 2022 | bo Mafa Primary Health Centre | 235 | 2796 | 143 | 83 | 100
October 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
October 2022 | bo Malakyariri Primary Health Centre | 30 | 1388 | 54 | 61 | 100
October 2022 | bo Gomari Primary Health Centre | 53 | 617 | 45 | 14 | 100
October 2022 | bo Chad Basin Development Authority Clinic | 152 | 2243 | 102 | 9 | 100
October 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
October 2022 | bo Nguwom Primary Health Center | 6 | 689 | 66 | 24 | 100
October 2022 | bo Maimusari Health Clinic | 44 | 519 | 225 | 8 | 100
October 2022 | bo Izge Primary Health Care Clinic | 21 | 873 | 153 | 22 | 100
October 2022 | bo Pompomari Primary Health Care Centre | 54 | 1030 | 71 | 16 | 100
October 2022 | bo Zabbarmari Health Clinic | 66 | 1028 | 125 | 27 | 100
October 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
October 2022 | bo Jakana Model Primary Health Care Center | 32 | 429 | 10 | 11 | 100
October 2022 | bo kaleri primary Health Centre | 5 | 737 | 39 | 217 | 100
October 2022 | bo Bama Maternal And Child Referral center | 21 | 873 | 153 | 22 | 100
November 2022 | bo Abbaganaram Maternal and Child Health Centre | 47 | 501 | 48 | 13 | 100
November 2022 | bo Bulabulin Primary Health Care Centre | 7 | 578 | 17 | 7 | 100
November 2022 | bo Mala Kachallah Primary Health Centre | 21 | 873 | 153 | 22 | 0
November 2022 | bo Dalori Primary Health Care Centre | 2 | 735 | 29 | 26 | 100
November 2022 | bo Mafa Primary Health Centre | 126 | 4797 | 189 | 50 | 100
November 2022 | bo Monguno Primary Health Care Center | 21 | 873 | 153 | 22 | 100
November 2022 | bo Malakyariri Primary Health Centre | 105 | 1005 | 86 | 59 | 100
November 2022 | bo Gomari Primary Health Centre | 61 | 558 | 43 | 17 | 100
November 2022 | bo Chad Basin Development Authority Clinic | 152 | 1486 | 131 | 14 | 100
November 2022 | bo Bama Skin Clinic | 21 | 873 | 153 | 22 | 100
November 2022 | bo Nguwom Primary Health Center | 7 | 279 | 76 | 40 | 100
November 2022 | bo Maimusari Health Clinic | 48 | 361 | 274 | 9 | 100
November 2022 | bo Izge Primary Health Care Clinic | 30 | 753 | 40 | 25 | 100
November 2022 | bo Pompomari Primary Health Care Centre | 18 | 1035 | 72 | 16 | 100
November 2022 | bo Zabbarmari Health Clinic | 18 | 1055 | 60 | 24 | 100
November 2022 | bo Banki Health Clinic | 21 | 873 | 153 | 22 | 0
November 2022 | bo Jakana Model Primary Health Care Center | 14 | 307 | 11 | 11 | 100
November 2022 | bo kaleri primary Health Centre | 23 | 708 | 125 | 100 | 100
November 2022 | bo Bama Maternal And Child Referral center | 21 | 873 | 153 | 22 | 100